## Sheet1
Existing Dependencies and Legacy Systems
Misaligned Accountability: There is a heavy reliance on legacy ARE-owned groups for Technology Solutions (TS)-owned work, which currently lacks alignment with the target Segment accountability model across SIT, DEV, PAT, and PROD environments.
Technical Debt: Legacy infrastructure access, specifically instances like VMC1 (Storm_ITS‑SDDE‑ep‑Appdeploy), remains active and must be decommissioned rather than migrated.
Process and Workflow Gaps
Onboarding Sequence Breakage: Migrating out of ARE groups without properly recreating the structured Application Deployment Access flow could leave users with incomplete tooling, such as missing PuTTY software or vital ServiceNow (SITAM_TDBFG_ITIL) roles.
Dependency Chain Breakage: Failing to secure ServiceNow and foundational Active Directory (AD) groups first will block all subsequent Windows, Unix, CyberArk, and SSH access, which completely prevents deployment capabilities.
Workflow Ambiguity: Currently, teams request Release Management (RM) support through IaP and MAA via ServiceNow (SN) DARM tickets, but the future-state routing for how these teams will receive and track their work remains undefined.
Security, Access, and Audit Risks
Workday and AD Disruption Risk: Organizational or internal mobility moves in Workday automatically trigger the removal of CyberArk/NPID access by design, meaning these moves must be carefully sequenced to avoid outages. Additionally, premature changes to AD groups risk a total loss of access for resources.
Premature Access Removal: There is a significant risk of losing critical access before the replacement groups are fully established and validated by the receiving segments.
Audit Findings Risk: If the access migration is not executed correctly, it will result in erroneous attestations, inevitably leading to audit findings. There are also current-state violations of least privilege and Segregation of Duties (SoD) that could pose vulnerabilities if access is not properly rationalized during the transition.
Resource Constraints
Personnel Shortages: There is a specific action item noting the need to secure a Business Systems Analyst (BSA) to assist with an ongoing P07 issue that is impacting the workflow.

## Sheet2
Axis / Risk Category | Specific Risk Factor | Risk Severity Score (1-10) | Justification
Dependencies & Legacy | Misaligned Accountability | 8 | Heavy reliance on legacy groups blocks the target accountability model.
Dependencies & Legacy | Technical Debt | 6 | Legacy infrastructure like VMC1 remains active and requires decommissioning.
Process & Workflow | Onboarding Breakage | 8 | Incomplete tooling blocks deployment engineering functions.
Process & Workflow | Dependency Chain Breakage | 10 | Completely prevents deployment capabilities if foundational AD groups are missed.
Process & Workflow | Workflow Ambiguity | 7 | Future-state routing for Release Management remains undefined.
Security & Audit | Workday / AD Disruption | 9 | High risk of automated access removal or total lockout if poorly sequenced.
Security & Audit | Premature Access Removal | 9 | Critical access could be lost before replacement groups are validated.
Security & Audit | Audit Findings Risk | 10 | Erroneous attestations will inevitably lead to formal audit findings.
Resource Constraints | Personnel Shortages | 7 | Existing in-flight issues are actively draining required resources.